## Release 3.5 (Actions)
Issue id | Issue key | Issue Type | Copado Story # | Issue key NEW (Rel 3) | VP's Comments 9/23 | Summary | Status | Assignee | P3 - UAT? | Comments (Dev) | (Story Points) | Assignee | (Developer) | Sprint
3521285 | SFDC-47502 | Task |  |  |  | DMX - Front End support | To Do |  |  |  | 8 | U512183 |  | Dearborn PNM 2024 Sp21
3495941 | SFDC-47138 | Task |  |  |  | Comms - Letter - Adjust Template ID for Appeal Denials related to terminations | To Do |  |  |  |  | U512507
3489866 | SFDC-47072 | Story |  |  |  | Portal - Process Logic - Configure the list of documents that a user can upload via the portal to align with the case type | To Do |  |  |  |  | U512507
3489851 | SFDC-47069 | Story |  |  |  | Portal - UI - Hide sensitive document types from Org Managers on cases | Analysis |  |  |  |  | U512507
3485795 | SFDC-47015 | Story |  |  |  | DocuSign - Process Logic - Generate DMX Associated Offices Form | Analysis |  |  |  |  | U512507
3485794 | SFDC-47014 | Story |  |  |  | DocuSign - Process Logic - Generate additional DMX Location Form and W9 | Analysis |  |  |  |  | U512507
3485784 | SFDC-47012 | Story |  |  |  | DocuSign - Process Logic - Generate additional DNOA Location Form and W9 | Blocked |  |  |  |  | U531504 | U531504
3476392 | SFDC-46828 | Task |  |  |  | Portal - UX - Implement breadcrumb navigation on launched app process | To Do |  |  |  | 5 | U512507
3476384 | SFDC-46827 | Task |  |  |  | Portal - UI - Remove additional click to submit comments | To Do |  |  |  |  | U512507
3473514 | SFDC-46787 | Story |  |  |  | LocationFormOS - Process Logic - Reactivate inactive facility if selected | Analysis |  |  |  |  | U512507
3473322 | SFDC-46782 | Story |  |  |  | Portal - UX - Add network disclaimers to recred application | Ready |  |  |  | 2 | U512507
3470688 | SFDC-46760 | Task |  | SFDC-47672 | Either you can use the original task or map to the new task | AppealOS - UI - Hide decision reasons from Org Manager portal users | In Progress | Shannon | No |  | 2 | U512507
3450234 | SFDC-46411 | Story |  |  |  | DocuSign - Action - Resend recred application packet for signature | Analysis |  |  |  |  | U512507
3450229 | SFDC-46410 | Story |  |  |  | DocuSign - Action - Resend application packet for signature | Analysis |  |  |  |  | U512507
3450224 | SFDC-46409 | Task |  |  |  | DocuSign - Process Logic - Capture submission and completion dates for application and DocuSign packets | To Do |  |  |  |  | U512507
3450223 | SFDC-46408 | Story |  |  |  | DocuSign - Process Logic - Email notification for signed/completed documents | Analysis |  |  |  |  | U512507
3450221 | SFDC-46407 | Story |  |  |  | CredAppOS - Process Logic - Do not commit changes made via Edit Blocks if user exits Portal App process | Ready |  |  |  | 5 | U531502
3450219 | SFDC-46406 | Task |  |  |  | Comms - Process Logic - Reference Code to generate letter instead of Network Name | To Do |  |  |  |  | U512507
3445403 | SFDC-46324 | Task |  |  |  | Org360 - Data Model - Remove Tax ID and Tax ID Type fields | Ready |  |  |  | 1 | U512507
3445402 | SFDC-46323 | Story |  |  |  | Recred - Process Logic - Move submitted application to â€œIn Progressâ€ | To Do |  |  |  |  | U512507
3436486 | SFDC-46143 | Story |  |  |  | Comms - Process Logic - Send NM Recred and OGM-related letters as certified mail | Blocked |  |  |  |  | U512507
3436485 | SFDC-46142 | Story |  |  |  | Comms - Process Logic - Send NM Application-related letters as certified mail | Blocked |  |  |  |  | U512507
3436481 | SFDC-46141 | Task |  |  |  | Portal - Process Logic - Create Account-Account Relationship record | To Do |  |  |  |  | U512507
3430339 | SFDC-46081 | Task |  |  |  | DocuSign - UI - Enable users to view and download DocuSign recred application documents | To Do |  |  |  |  | U531504
3430336 | SFDC-46080 | Story |  |  |  | DocuSign - Process Logic - Generate recred app packets | Analysis |  |  |  |  | U531504 | U531504
3430335 | SFDC-46079 | Story |  |  |  | DocuSign - Process Logic - Generate DMX packets by app type | Analysis |  |  |  |  | U531504
3427176 | SFDC-46013 | Task |  | SFDC-47672 | Either you can use the original task or map to the new task | LocationFormOS - Process Logic - Capture Primary Contact for new facility without updating organization contact | In Progress | Subhani | Yes |  | 1 | U533779 |  |  | Changed the JIRA sprint from 3.5 to 3
3415242 | SFDC-45754 | Story |  |  |  | Portal - UX - Brand the recred application for the specific network | Ready |  |  |  | 3 | U512507
3411119 | SFDC-45702 | Task |  |  |  | Recred - Process Logic - Track/store if a provider removed contact info via the Portal App | In Progress | Amruta | No |  | 1 | U532642
3410782 | SFDC-45692 | Story |  | SFDC-47672 |  | Cred - Process Logic - Set DMX Effective To date on OGM/recred terms to last day of month | In Progress | Subhani | Yes |  | 5 | U533779 | U531502
3410109 | SFDC-45679 | Task |  |  |  | Facility360 - Process Logic - Enable Dental Data Analysts to create fee schedules | In Progress | Amruta | No |  | 1 | U532642 | U532644
3409995 | SFDC-45673 | Task |  |  |  | Recred - Process Logic - Close Group Recredentialing case when all related cases are closed | Ready |  |  |  | 1 | U512507
3398565 | SFDC-45462 | Story |  |  |  | Portal - Action - Initiate self-service action to add locations as Org Manager | In Progress |  | No |  | 5 | U512507
3398562 | SFDC-45461 | Story |  |  |  | Portal - Action - Submit appeal case as Org Manager | Ready |  |  |  | 8 | U512507
3398561 | SFDC-45460 | Story |  |  |  | Portal - Action - Submit recredentialing application as Org Manager | Ready |  |  |  | 8 | U512507
3398560 | SFDC-45459 | Story |  |  |  | Portal - Action - Submit application as Org Manager | In Progress |  | No |  | 8 | U532642
3398559 | SFDC-45458 | Story |  |  |  | QC - Process Logic - Randomly select Application cases to assign to QC queue | Analysis |  |  |  |  | U512507
3369459 | SFDC-45120 | Story |  |  |  | QC - Process Logic - Move Application cases forward that are not randomly selected for QC | Analysis |  |  |  |  | U512507
3363399 | SFDC-45026 | Story |  |  |  | Portal - Action - Initiate self-service action to add locations as Provider | In Progress |  | No |  | 5 | U512507
3348481 | SFDC-44793 | Story |  |  |  | Recred - Integration Action - Send extract every 30 days of providers with upcoming recred due dates | Blocked |  |  |  |  | U512507
3348480 | SFDC-44792 | Story |  |  |  | Recred - Integration Action - Send weekly extract of providers with completed applications to CVO | Blocked |  |  |  |  | U512507
3348479 | SFDC-44791 | Story |  | SFDC-47672 |  | Recred - Action - Enable Credentialing Specialist to move case to â€œReady for CVOâ€ | Done |  | Yes | CardProviderActions-Flexcard and Integrationprocedure | 2 | U402162 | U532644 | Dearborn PNM 2024 Sp14
3339081 | SFDC-44663 | Story |  |  |  | Recred - Process Logic - Track if contact info changes via Portal App were made by provider | In Progress |  | No |  | 2 | U532641
3329500 | SFDC-44555 | Story |  | SFDC-47672 |  | RecredAppOS - Process Logic - Enable provider to report that Board Cert should be removed on Recred App | In Progress |  | Yes |  | 1 | U532641
3328939 | SFDC-44542 | Story |  |  |  | Case - List View - Update Dental Director queue list views | Done |  | No |  | 2 | U434560 | U532644 | Dearborn PNM 2024 Sp11
3317358 | SFDC-44371 | Story |  |  |  | Cred - Process Logic - Select FTCA coverage for providers operating under IHS | Analysis |  |  |  |  | U512507
3315619 | SFDC-44358 | Story |  |  |  | QC - Process Change - Placeholder for application processing optimization opportunities | To Do |  |  |  |  | U512507
3295510 | SFDC-44088 | Story |  |  |  | QC - Process Logic - Name facility in Chatter note for clarity | In Progress |  | No |  | 2 | U533779 | U531502
3295509 | SFDC-44087 | Task |  |  |  | Recred - Batch Job - Adjust running user to generic admin user | To Do |  |  |  |  | U512507
3294093 | SFDC-44068 | Story |  | SFDC-47672 |  | Recred - Process Logic - Add "In Progress" status | Done |  | Yes | If not deployed, we might see issue with In progress button | 1 | U539547 |  | Dearborn PNM 2024 Sp10
3285632 | SFDC-43954 | Task |  |  |  | Recred - Data Migration - Migrate all provider recredentialing due dates | To Do |  |  |  |  | U512183
3285384 | SFDC-43950 | Story |  | SFDC-47672 |  | CredAppOS - UI - Only permit the creation of licenses related to the state of the application | Done |  | Yes |  | 2 | U539547 | U531504 | Dearborn PNM 2024 Sp10
3285370 | SFDC-43948 | Story |  | SFDC-47672 |  | RecredAppOS - UI - Allow user to upload Application | Done |  | Yes |  | 1 | U402162 |  | Dearborn PNM 2024 Sp10
3272239 | SFDC-43787 | Story |  |  |  | Comms - Email - URAC Term | Analysis |  |  |  |  | U512507
3272237 | SFDC-43786 | Story |  | SFDC-47672 |  | Comms - Email - Recredentialing Success | In Progress |  | Yes | Case After Save Flow | 3 | U533779
3272233 | SFDC-43783 | Story |  | SFDC-47672 |  | Comms - Email - Recredentialing Appeal Approval - No Break in Coverage | In Progress |  | Yes | Case After Save Flow | 3 | U532641 | U532636
3272232 | SFDC-43782 | Story |  | SFDC-47672 |  | Comms - Email - Recredentialing Appeal Approval - Break in Coverage | In Progress |  | Yes | Case After Save Flow | 3 | U532641
3272221 | SFDC-43779 | Story |  |  |  | Comms - Letter - Complete Recredentialing Application Received | Blocked |  |  |  |  | U512507
3265728 | SFDC-43692 | Story |  | SFDC-47672 |  | RecredAppOS - UI - Allow user to upload Other Supporting Documents | Done |  | Yes |  | 2 | U429380 |  | Dearborn PNM 2024 Sp09
3249074 | SFDC-43432 | Story |  |  |  | QC - Process Change - Update data issue values and mapping to each step | To Do |  |  |  |  | U512507
3248832 | SFDC-43407 | Story |  |  |  | Recred - Integration - Process recredentialing files from CVO | To Do |  |  |  |  | U512507
3248830 | SFDC-43405 | Story |  |  |  | CCB-IN PROGRESS-Provider 360 - UI - Adjust additional object page layouts to be read only | In Progress |  | No |  | 2 | U532641
3224507 | SFDC-42969 | Story |  |  |  | Case - Record Type - Add "Group Recredentialing" case | Done |  | No |  | 1 | U431373 | U532644 | Dearborn PNM 2024 Sp07
3212204 | SFDC-42804 | Story |  | SFDC-47672 |  | Comms - Letter - Recredentialing Acknowledgement - NM | Done |  | Yes |  | 2 | U434560 |  | Dearborn PNM 2024 Sp10
3207963 | SFDC-42750 | Story |  | SFDC-47672 |  | Recred - Action - Launch "Recred App" process from case | Done |  | Yes | If Yes, create a Task - Hide the button on the cardProviderActions flexcard | 3 | U429380 | U532644 | Dearborn PNM 2024 Sp07
3201046 | SFDC-42627 | Story |  |  |  | QC - Process Logic - QC applications submitted by providers via portal | To Do |  |  |  |  | U512507
3201043 | SFDC-42624 | Story |  |  |  | RecredAppOS - UI - Configure step to specify DocuSign packet recipients | In Progress |  | No | Recommit components | 2 | U532642 | U531504
3192914 | SFDC-42512 | Story |  |  |  | Comms - Email - Complete Recredentialing Application Received | Ready |  |  |  | 3 | U512507
3188743 | SFDC-42431 | Story |  | SFDC-47672 |  | RecredAppOS - UI - Configure "General Info" step | Done |  | Yes | Dependent on 42750 | 3 | U402162 |  | Dearborn PNM 2024 Sp07
3188472 | SFDC-42430 | Story |  | SFDC-47672 |  | RecredAppOS - UI - Allow user to enter supporting details on "Professional Questions" step | Done |  | Yes | Dependent on 42750 | 5 | U429380 | U531504 | Dearborn PNM 2024 Sp08
3188464 | SFDC-42429 | Story |  | SFDC-47672 |  | Recred - Fields - Manage recredentialing cycle dates by provider | Done |  | Yes | Task - Remove UI component from the page layout. With 3.5 need to cleanup the data and add the Recred cycle flexcard back to UI | 8 | U535321 | U531502 | Dearborn PNM 2024 Sp08
3188456 | SFDC-42426 | Story |  |  |  | Recred - Batch Job - Mass create on-cycle recredentialing cases | Done |  | No | With 3.5 need to cleanup the data and add the Recred cycle flexcard back to UI | 8 | U429380 | U532644 | Dearborn PNM 2024 Sp07
3081102 | SFDC-41085 | Story |  |  |  | Comms - Email - Recredentialing Acknowledgement | Ready |  |  |  | 3 | U512507
3080861 | SFDC-41060 | Story |  | SFDC-47672 |  | Comms - Letter - Recredentialing Success - NM | Done |  | Yes | Case After Save Flow | 5 | U434560 |  | Dearborn PNM 2024 Sp10
2927996 | SFDC-39099 | Story |  | SFDC-47672 |  | Comms - Letter - Recredentialing Appeal Approval - No Break in Coverage - NM | In Progress |  | Yes | Case After Save Flow | 2 | U532641 | U532636
2927991 | SFDC-39098 | Story |  | SFDC-47672 |  | Comms - Letter - Recredentialing Appeal Approval - Break in Coverage - NM | In Progress |  | Yes | Case After Save Flow | 3 | U532641 | U532636
2887618 | SFDC-38446 | Story |  | SFDC-47672 |  | Comms - Letter - URAC Term - NM | In Progress |  | Yes | Case After Save Flow | 5 | U532641
2851135 | SFDC-38075 | Story |  |  |  | Case - Action - Mass update cases to "Approved" | Done |  | No | Recommit | 3 | U431373 | U531504 | Dearborn PNM 2024 Sp13
| NEW |  |  | SFDC-47673 |  | Recred - Hide "Recred App" button and Table |  |  | Yes

## Info
If no deployment
1 | If omnistudio, the deployment will not fail but the processes will fail
2 | If non-omnistudio components, it will fail and caught during deployment itself
3 | If DR is new with these stories, will fail the UI process saying bundle does not exists
If deployed and they don't want the functionality
Will require those changes whether UI or Processes etc.

## Release 3 (Actions)
Issue key | Copado Story # | Issue key NEW (Rel 3) | Team | EPIC | Sprint | Summary | Priority | Fix Version/s | Ready to Promote | Update JIRA with (for Scott) | Copado Updates - Status
SFDC-41061 |  | SFDC-47672 | FALSE | Recredentialing | Dearborn PNM 2024 Sp13 | Comms - Letter - Recredentialing Involuntary Termination - NM | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-41762 |  |  | sfdc_pnm_team1a | Recredentialing |  | List View - Update "My Pending Cases" filter to include Recredentialing cases | Low | SF DB PNMRel3 | N/A | Deployed to PROD | No Action either in JIRA or Copado
SFDC-41937 |  |  | sfdc_pnm_team1a | Recredentialing |  | List View - Add "Type" column to Recredentialing list views | Low | SF DB PNMRel3 | N/A | Deployed to PROD | No Action either in JIRA or Copado
SFDC-42432 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp07 | RecredAppOS - UI - Configure basic OS setup | High | SF DB PNMRel3 | N/A | No copado story | No Action either in JIRA or Copado
SFDC-42979 |  | SFDC-47672 | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp10 | Recred - Process Logic - Deactivate Provider Date Config record when provider is termed | High | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-43461 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp08 | Document Upload - Process Logic - Capture the state associated with an uploaded license/certificate from case | High | SF DB PNMRel3 | Yes
SFDC-43616 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp09 | Document Upload - Process Logic - Capture the case associated with the uploaded document | High | SF DB PNMRel3 | Yes
SFDC-43754 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp10 | Document Upload - Process Logic - Capture the state associated with an uploaded license/certificate from info change process | High | SF DB PNMRel3 | Yes
SFDC-43944 |  | SFDC-47672 | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp12 | RecredAppOS - Process Logic - Prefill values in application | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-43945 |  | SFDC-47672 | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp10 | RecredAppOS - Process Logic - Display related files on Attachments step | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-43946 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp10 | CredAppOS - Process Logic - Display related files on Attachments step | Medium | SF DB PNMRel3 | Yes | Moved as part of different story | No Action either in JIRA or Copado
SFDC-43949 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp11 | RecredAppOS - Process Logic - Enforce responses to Board Cert questions | Low | SF DB PNMRel3 | Yes | Moved as part of different story | No Action either in JIRA or Copado
SFDC-43951 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp12 | Portal - Button Access - Provide internal users temporary access to portal actions | Low | SF DB PNMRel3 | No |  | No Action either in JIRA or Copado
SFDC-44169 |  |  | sfdc_pnm_team1a | Recredentialing |  | Change the length of DateOfFormat Field on STG_CVO_Integration to be able to accept Date/Time format | High | SF DB PNMRel3 | Yes
SFDC-44513 |  |  | sfdc_pnm_team1b | Recredentialing | Dearborn PNM 2024 Sp11 | Lead - Packet Upload logic | High | SF DB PNMRel3 | 1B | Team1B Story
SFDC-44535 |  | SFDC-47672 | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp11 | RecredAppOS - UI - Add "Cancel" button to portal recred app process | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-44549 |  | SFDC-47672 | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp11 | Recred - UI - Add â€œDEA Waiverâ€ internal recred process attachment options | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done
SFDC-44592 |  |  | sfdc_pnm_team1a | Recredentialing | Dearborn PNM 2024 Sp11 | AppealOS - UI - Allow user to upload Other Supporting Documents | High | SF DB PNMRel3 | Yes
SFDC-45457 |  | SFDC-47672 | FALSE | Recredentialing | Dearborn PNM 2024 Sp15 | Comms - Letter - Recredentialing Involuntary Termination | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5 | Done

## Release 4 (Actions)
Issue key | Issue id | Issue Type | Copado Story # | Issue key NEW (Rel 3) | Summary | Status | Sub-task | Has Copdo Story | Ready to Promote | Comments | Sprint | Copado Updates - Status
SFDC-47140 | 3495991 | Story |  |  | Update Org Details - Process Logic - Enable user to update "Is Delegated?" flag | Blocked |  | No
SFDC-46999 | 3484422 | Task |  |  | DSO - Data - Upload revised delegated DSO fee schedule files | To Do
SFDC-46719 | 3466333 | Story |  |  | DSO - Process Logic - Assign effective date to new facilities and/or affiliations | Ready |  | No
SFDC-46492 | 3455720 | Task |  |  | DSO - Process Logic - Prevent multiple emails after DSO process | In Progress |  | Yes | No
SFDC-45987 | 3426100 | Task |  |  | DSO - Process Logic - Capture load and data errors on staging record | In Progress |  | No
SFDC-45680 | 3410110 | Task |  | SFDC-47672 | Info Change - Process Logic - Update unclear selections on "Update Provider Details" | In Progress |  | Yes | Yes
SFDC-45517 | 3401451 | Story |  |  | DSO - Process Logic - Notify account owner when data load procedure is complete | Done | 46352, 46413 | Yes | No |  | Dearborn PNM 2024 Sp16
SFDC-45464 | 3398570 | Story |  | SFDC-47672 | Org/Facility Info Change - Process Logic - Do not commit changes made via Edit Blocks if user exits process | In Progress | 45665 | Yes | Yes
SFDC-45130 | 3370334 | Story |  |  | DSO - Process Logic - Assign payer participations to new affiliation based on network | Done | 45738, 46254, 46263, 46331, 46335, 46350 | Yes | No |  | Dearborn PNM 2024 Sp16
SFDC-44981 | 3362108 | Task |  | SFDC-47672 | Provider360 - Process Logic - Update DEA related selections on Update Provider Details | In Progress |  | Yes | Yes
SFDC-44971 | 3361780 | Story |  |  | DSO - Process Logic - Assign fee schedule to new facility based on organization & zip code | Done | 46419, 46479 | Yes | No |  | Dearborn PNM 2024 Sp16
SFDC-44816 | 3350240 | Story |  |  | DSO - Report - View DSO file import successes and errors | In Progress |  | Yes | No
SFDC-44815 | 3350236 | Story |  |  | DSO - Process Logic - Notify account owner when a new file is ready for review | Ready |  | No
SFDC-44814 | 3350235 | Story |  |  | Portal - Report - View DSO file import successes and errors | In Progress |  | Yes | No
SFDC-44658 | 3338469 | Story |  |  | LocationFormOS - Process Logic - Enable user to document if the facility serves tribal members and/or is associated with IHS | Analysis
SFDC-44590 | 3332034 | Story |  |  | DSO - Action - Enable user to launch import process from account | Done |  | Yes | No | Remove button from practice record page | Dearborn PNM 2024 Sp15
SFDC-44547 | 3328956 | Story |  |  | CredAppOS - Process Logic - Enable user to proceed with any active state license when app is associated with tribal nation | Analysis
SFDC-44534 | 3328902 | Story |  |  | Cred - Process Logic - Enable user to document Expiration Date associated with DEA waiver | To Do
SFDC-44099 | 3295523 | Story |  |  | DSO - Process Logic - Load Add data into the appropriate PNM objects | Done | 45577, 45735, 45737, 45903, 45966, 46112 | Yes | No |  | Dearborn PNM 2024 Sp15
SFDC-44093 | 3295516 | Story |  |  | DSO - UI - Enable user to view and edit Add data | Done | 45752, 46329 | Yes | No |  | Dearborn PNM 2024 Sp16
SFDC-44091 | 3295514 | Story |  |  | DSO - Data Model - Configure staging object for DSO data transformation | Done | 45277, 45743, 46057, 46058, 46059, 46107 | Yes | No |  | Dearborn PNM 2024 Sp15
SFDC-43646 | 3263261 | Task |  |  | Info Change - Process Logic - Update Healthcare Provider names when parent Account name changes | To Do
SFDC-43642 | 3263249 | Story |  | SFDC-47672 | Update Supporting Docs - Process Logic - Do not commit changes made via Edit Blocks if user exits process | In Progress |  | Yes | Yes
SFDC-43577 | 3260604 | Story |  | SFDC-47672 | Provider Info Change - Process Logic - Do not commit changes made via Edit Blocks if user exits process | In Progress |  | Yes | Yes
SFDC-43418 | 3249055 | Task |  | SFDC-47672 | CredAppOS - Process Logic - Adjust CAQH ID validation logic | In Progress |  | Yes | Yes
SFDC-42909 | 3219872 | Story |  |  | DSO - Action - Enable user to add existing provider to existing facility from org account | To Do
SFDC-41069 | 3080880 | Story |  |  | Prompt users to indicate if they want to send communication to confirm Directory Validation changes | In Test |  | Yes | N/A | Deployed to PROD
SFDC-45665 |  | SubTask |  | SFDC-47672

## Scott
Issue key | Summary | Priority | Fix Version/s | Ready to Promote | Update JIRA with
SFDC-41061 | Comms - Letter - Recredentialing Involuntary Termination - NM | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-41762 | List View - Update "My Pending Cases" filter to include Recredentialing cases | Low | SF DB PNMRel3 | N/A | Deployed to PROD
SFDC-41937 | List View - Add "Type" column to Recredentialing list views | Low | SF DB PNMRel3 | N/A | Deployed to PROD
SFDC-42432 | RecredAppOS - UI - Configure basic OS setup | High | SF DB PNMRel3 | N/A | No copado story
SFDC-42979 | Recred - Process Logic - Deactivate Provider Date Config record when provider is termed | High | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-43461 | Document Upload - Process Logic - Capture the state associated with an uploaded license/certificate from case | High | SF DB PNMRel3 | Yes
SFDC-43616 | Document Upload - Process Logic - Capture the case associated with the uploaded document | High | SF DB PNMRel3 | Yes
SFDC-43754 | Document Upload - Process Logic - Capture the state associated with an uploaded license/certificate from info change process | High | SF DB PNMRel3 | Yes
SFDC-43944 | RecredAppOS - Process Logic - Prefill values in application | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-43945 | RecredAppOS - Process Logic - Display related files on Attachments step | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-43946 | CredAppOS - Process Logic - Display related files on Attachments step | Medium | SF DB PNMRel3 | Yes | Moved as part of different story
SFDC-43949 | RecredAppOS - Process Logic - Enforce responses to Board Cert questions | Low | SF DB PNMRel3 | Yes | Moved as part of different story
SFDC-43951 | Portal - Button Access - Provide internal users temporary access to portal actions | Low | SF DB PNMRel3 | No
SFDC-44169 | Change the length of DateOfFormat Field on STG_CVO_Integration to be able to accept Date/Time format | High | SF DB PNMRel3 | Yes
SFDC-44513 | Lead - Packet Upload logic | High | SF DB PNMRel3 | 1B | Team1B Story
SFDC-44535 | RecredAppOS - UI - Add "Cancel" button to portal recred app process | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-44549 | Recred - UI - Add â€œDEA Waiverâ€ internal recred process attachment options | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5
SFDC-44592 | AppealOS - UI - Allow user to upload Other Supporting Documents | High | SF DB PNMRel3 | Yes
SFDC-45457 | Comms - Letter - Recredentialing Involuntary Termination | Medium | SF DB PNMRel3 | Yes | Move to Release 3.5